## Intro
4th Year Software Test Plan
Project Name | Login Console
Project Manager | Naomi Hurley
Prepared by | Naomi Hurley and the 4th year Computing students
Tech Lead | To be confirmed
Date
Revision History
Revision | Author | Comment
1 | Naomi Hurley | Initial Draft

## Product No 1 or Sprint No 1
|  | Purpose: | Test Advanced Data Centric Project
Final run through of the entire application |  |  |  | Windows 10
Requirement ID | Sprint | Test Case Ref | Test Case Name | Descriptions | Search Parameters / Instructions | Checks | Expected Result | Actual Result | Results Pass/Fail | Bug # | Comments
1 | 1 | TC.001 | Page Navigation | Nav | 1. Launch Application 2. Click links on tool bar | Checks if user can navigate throught the pages | User can navigate | User can navigate through the pages | Pass
2 | 1 | TC.002 | List Pages | Data | 1. Launch Application 2. Click e.g Show books | Checks if list data is being displayed it | Data Should be displayed | Data is being displayed | Pass
3 | 1 | TC.003 | Add Book | Data | 1. Launch Application 2. Click add book 3. Enter Test Data 4.See if data is added | Checks if you can add a book to the database | Book should be added | Book is add to the database | Pass
4 | 1 | TC.004 | Error Handling | book error | 1. Launch Application 2. Click add book 3. Enter no Test Data | Checks if an error is displayed next to input box | error should be displayed | Error is displayed | Pass
5 | 1 | TC.005 | Add customer | Data | 1. Launch Application 2. Click add Customer 3. Enter Test Data 4.See if data is added | Checks if you can add a customer to the database | customer should be added | customer is add to the database | Pass
6 | 1 | TC.006 | Error Handling | Customer error | 1. Launch Application 2. Click add customer 3. Enter no Test Data | Checks if an error is displayed next to input box | error should be displayed | Error is displayed | Pass
7 | 1 | TC.007 | Add Loan | Data | 1. Launch Application 2. Click add loan 3. Enter Test Data 4.See if data is added | Checks if you can add a loan to the database | loan should be added | loan is add to the database | Pass
8 | 1 | TC.008 | Error Handling | Data | 1. Launch Application 2. Click add loan 3. Enter Invalid customer id and valid book ID 4.See if error is displayed 5.Enter valid customer id and invalid book ID 6.See if error is displayed 7.Enter invalid customer id and invalid book ID 8.See if error is displayed | Checks if an appropriate Error is displayed | An error should be displayed related to the invalid data that was entered | Appropriate Error was displayed on the error page | Pass
9 | 1 | TC.009 | Login | Login | 1. Launch Application 2. Click any of the links 3. Enter user for the username and user for the password | Checks if the user can login in | User should be able to log in | User can login | Pass
10 | 1 | TC.010 | Log out | Log out | 1. Launch Application 2. Click any of the links 3. Enter user for the username and user for the password 4. Go to List Books 5. Click Log out | Checks if the user can log out | User should be able to log out | User can log out | Pass

## Product No 2 or Sprint No 2
|  | Purpose: | This set of tests is intended to check main functionality developed
Test Run Title e.g. Login validation |  |  |  | Microsoft Internet Explorer 9 Windows 7 Microsoft Internet Explorer 10 Windows 7 Micresoft Internet Explorer 11 Windows 7 Microsoft Internet Explorer 8 Windows XP Microsoft Internet Explorer 7 Windows XP Firefox latest version Apple Safari Windows XP Apple Safari Google Chrome Windows XP Opera Windows XP
Requirement ID | Sprint | Test Case Ref | Test Case Name | Descriptions | Search Parameters / Instructions | Checks | Results Pass/Fail | Bug # | Comments

## Test Progress
Tabs | Developped by | No of test cases | Tester | No of days | Browsers | Test cases passed | Test cases failed | To be done | Percentage done
Sprint No
Test Run description | Team A | 18 |  |  | All | 0 | 0 | 18 | 0%
Test Run description | Team B | 8 |  |  | N/A | 0 | 0 | 8 | 0%
Test Run description | Team C | 19 |  |  | All | 0 | 0 | 19 | 0%
Test Run description | Team D | 20 |  |  | All | 0 | 0 | 20 | 0%
Test Run description | Team C | 42 |  |  | All | 0 | 0 | 42 | 0%
Total |  | 107 |  |  |  |  | 0 | 0 | 0%