## Intro
4th Year Software Test Plan
Project Name | Login Console
Project Manager | Naomi Hurley
Prepared by | Naomi Hurley and the 4th year Computing students
Tech Lead | To be confirmed
Date
Revision History
Revision | Author | Comment
1 | Naomi Hurley | Initial Draft

## Product No 1 or Sprint No 1
|  | Purpose: | Test Advanced Data Centric Project
Final run through of the entire application |  |  |  | Windows 10
Requirement ID | Sprint | Test Case Ref | Test Case Name | Descriptions | Search Parameters / Instructions | Checks | Expected Result | Actual Result | Results Pass/Fail | Bug # | Comments
1 | 1 | TC.001 | Icons Displaying | GUI | 1. Launch Application | Checks if the app logo is displayed on the splash screen | Logo is displayed on the splash screen | Logo was displayed when I launched the application | Pass
2 | 1 | TC.002 | Download data | Data | 1. Launch Application | checks if Game Stats are downloaded in the Background as the app is loading | Games stats are downloaded | Game stats are downloaded and displayed in the console window for debugging and in the Game Stats page | Pass
3 | 1 | TC.003 | View Game Stats | GUI | 1. Launch Application 2. Click View Game Statistics | Checks if you can see game history and statistics | Game Stats are displayed in a list view | Game stats are there to view | Pass
4 | 1 | TC.004 | Refresh Game Stats | GUI | 1. Launch Application 2. Create new game 3.Enter Details 4.Start New Game 5. Finish Game 6. Return to Game Statistic Page and click refresh | Checks if you can see new game stats after completing a game | New Game Stats are displayed | Game stats are there to view | Pass
5 | 1 | TC.005 | Checkout Data Downloaded | Data | 1. Launch Application 2. Click Create New Game | Checks if Checkout Data is downloaded from MONGO | Data Downloaded and outputed to console | Checkout Data is downloaded and outputted to console for debugging | Pass
6 | 1 | TC.006 | User Input | Data | 1. Launch Application 2. Click Create New Game 3. Click Start new Game with missing values | Checks if alert is displayed if 1 or more values is missing | Alert pops up | Alert did display alerting the user that all values must be filled in | Pass
7 | 1 | TC.007 | Player Win | GUI | 1. Launch Application 2. Click Create New Game 3. Enter all values 4. Make one player win the sets | Checks if a player can win the match | Alert pops up saying who won | Alert did display alerting the user that the match is over and who won | Pass
8 | 1 | TC.008 | Backup File | Data | 1. Launch Application 2. Click Create New Game 3. Enter all values 5.Click Start new game | Checks if checkout data is retrieved from a backup file if there is no internet connection | Data should be seen in the console window | Data is seen in the console window | Pass

## Product No 2 or Sprint No 2
|  | Purpose: | This set of tests is intended to check main functionality developed
Test Run Title e.g. Login validation |  |  |  | Microsoft Internet Explorer 9 Windows 7 Microsoft Internet Explorer 10 Windows 7 Micresoft Internet Explorer 11 Windows 7 Microsoft Internet Explorer 8 Windows XP Microsoft Internet Explorer 7 Windows XP Firefox latest version Apple Safari Windows XP Apple Safari Google Chrome Windows XP Opera Windows XP
Requirement ID | Sprint | Test Case Ref | Test Case Name | Descriptions | Search Parameters / Instructions | Checks | Results Pass/Fail | Bug # | Comments

## Test Progress
Tabs | Developped by | No of test cases | Tester | No of days | Browsers | Test cases passed | Test cases failed | To be done | Percentage done
Sprint No
Test Run description | Team A | 18 |  |  | All | 0 | 0 | 18 | 0%
Test Run description | Team B | 8 |  |  | N/A | 0 | 0 | 8 | 0%
Test Run description | Team C | 19 |  |  | All | 0 | 0 | 19 | 0%
Test Run description | Team D | 20 |  |  | All | 0 | 0 | 20 | 0%
Test Run description | Team C | 42 |  |  | All | 0 | 0 | 42 | 0%
Total |  | 107 |  |  |  |  | 0 | 0 | 0%